## MIGRATION_STATUS_MASTER_v2
Origin Controller | Original URL | HTTP Method | Source File Path | DMZ File Path | New URL | New Method | Data Origin | ControllerTasks | Mapping&BodyTasks | WrapperTasks | Migration Status | Commit Hash | Migrated Date | Notes
CreditController | credit/getClienteFactura/{cliente}/{factura} | GET | WebApiMagento/Controllers/CreditController.cs:69 | WebApiMagento/Controllers/CreditController.cs:44 | credit/getClienteFactura/{cliente}/{factura} | POST | SAP (TZ01 ZAPI_TZ01_ZSPLIT_MERC) | 100.00% | 100.00% | 100.00% | Migrated | 9ec6be1 | 2026-07-24 | Bridge at DMZ CreditController.cs:51. Verb changed GET?POST, called as PostSAP(..., "{}") with an empty body. See G-04.
CreditController | credit/getClienteSaldo/{cliente} | GET | WebApiMagento/Controllers/CreditController.cs:98 | WebApiMagento/Controllers/CreditController.cs:19 | partner/client/{clientId} | GET | SAP (BP05 ? Zcrmimporte, ZlimCred) | 0.00% | 0.00% | 100.00% | In Progress | 8c5248a |  | master_migration_summary_unified.md §2.3 reports CheckClientBalance complete on SAP; DMZ still calls curl.Get to LAN.
CreditController | credit/MonederoSaldoCredito | POST | WebApiMagento/Controllers/CreditController.cs:468 | WebApiMagento/Controllers/CreditController.cs:226 | customer/wallet/details | POST | SAP (SD18) | 50.00% | 100.00% | 100.00% | In Progress | 8c5248a |  | Estimated 9/17/30 days, Dev 2 — critical path. Note the estimate treats this as unbuilt while the summary claims monedero complete; see G-08.
CreditController | credit/getSms | POST | WebApiMagento/Controllers/CreditController.cs:25 | WebApiMagento/Controllers/CreditController.cs:68 | Unknown | Unknown | ANDROID (TcAAEA00030_EnvioMensajes) |  |  |  | Planed Dev 1 | 8c5248a |  | Estimated 1/2/3 days, Dev 1. Local DB stays permanently — not a SAP target.
CreditController | credit/validateSms | POST | WebApiMagento/Controllers/CreditController.cs:47 | WebApiMagento/Controllers/CreditController.cs:99 | (internal) IsValidated |  | SAP (BP05) + ANDROID | 0.00% | 0.00% | 50.00% | In Progress | 8c5248a |  | Cross-validation implemented in BusinessPartnerMethods.GetClient + MAVIANDROID01; no DMZ-facing route.
CreditController | credit/codigoPromocion | POST | WebApiMagento/Controllers/CreditController.cs:125 | WebApiMagento/Controllers/CreditController.cs:127 | Unknown | Unknown | EXT (SuccessFactors / Sigmavi) | 0.00% | 0.00% | 50.00% | Not Migrated | 8c5248a |  | API SAP SUCCESSFACTOR + BP05 + SIGMAVI
CreditController | credit/codigoRecomendado | POST | WebApiMagento/Controllers/CreditController.cs:237 | WebApiMagento/Controllers/CreditController.cs:185 | Unknown | GET | INTELISIS (BP05) | 0.00% | 0.00% | 100.00% | In Progress | 8c5248a |  | Estimated 1/2/3 days, Dev 1.
CreditController | credit/ExistRFCAndPhoneCte | POST | WebApiMagento/Controllers/CreditController.cs:375 | WebApiMagento/Controllers/CreditController.cs:382 | (building block) partner/client/filter/{sapFilter} | GET | BP05, SuccesFactor, SD36, SD05 | 0.00% | 0.00% | 50.00% | Planed Dev 1 | 8c5248a |  | Son 4 controllers, 4 Mappings y 2 nuevos Wrappers (BP05, SuccesFactor, SD36, SD05)
CreditController | credit/getPlazos | GET | WebApiMagento/Controllers/CreditController.cs:580 | WebApiMagento/Controllers/CreditController.cs:432 | Unknown | Unknown | SAP (SD40 ) + SIGMAVI (CondicionesCredVtaLinea) | 0.00% | 0.00% | 0.00% | To Plan | 8c5248a |  | Wrapper SD40 + Sigmavi logic
CreditController | credit/getCreditAccount/{pAccount} | GET | WebApiMagento/Controllers/CreditController.cs:438 | WebApiMagento/Controllers/CreditController.cs:273 | partner/client/filter/{sapFilter} | GET | INTELISIS | 0.00% | 0.00% | 0.00% | To Plan | 8c5248a |  | BP05 o zapi_bp05ma
CreditController | credit/GetUnificationWalletStatus | POST | WebApiMagento/Controllers/CreditController.cs:489 | WebApiMagento/Controllers/CreditController.cs:240 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | 8c5248a |  | Account-unification family; not enumerated in the gap estimates.
CreditController | credit/CheckAccountsPreUnification | POST | WebApiMagento/Controllers/CreditController.cs:506 | WebApiMagento/Controllers/CreditController.cs:248 | Unknown | Unknown | INTELISIS + (BP05) | 0.00% | 0.00% | 0.00% | Not Migrated | 8c5248a |  | cteEnciarA (AccountType method)
CreditController | credit/SetUnificationWalletData | POST | WebApiMagento/Controllers/CreditController.cs:524 | WebApiMagento/Controllers/CreditController.cs:256 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | 8c5248a |  | INTELISIS SP SpCREDIDatosSolicitudCreditoArt / INSERT INTO CREDIHUnificacionMonedero (IdEcommerce, ClienteCredito, ClienteContado, FechaRegistro) VALUES (@IdEcommerce, @ClienteCredito, @ClienteContado, GETDATE()) / cteEnciarA (AccountType method)
CreditController | credit/SolicitudMercancia | POST | WebApiMagento/Controllers/CreditController.cs:559 | WebApiMagento/Controllers/CreditController.cs:318 | Unknown | Unknown | ANDROID | 0.00% | 0.00% | 0.00% | Planed Dev 1 | 8c5248a |  | Es android
CreditController | credit/guardardocumento | POST | WebApiMagento/Controllers/CreditController.cs:591 | WebApiMagento/Controllers/CreditController.cs:442 | Unknown | Unknown | EXT (Hazten document store) |  |  |  | Planed Dev 1 | 8c5248a |  | Added 2026-07-13 by Uriel Valencia; document-image service, not an Intelisis dependency.
CreditController | credit/SaveHaztenTransaction | POST | WebApiMagento/Controllers/CreditController.cs:424 | WebApiMagento/Controllers/CreditController.cs:264 | Unknown | Unknown | EXT (Hazten) |  |  |  | Out of scope | 8c5248a |  | As above.
CreditController | credit/CreditoWeb_FormDatos | POST | WebApiMagento/Controllers/CreditController.cs:144 | WebApiMagento/Controllers/CreditController.cs:141 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana. Explicitly excluded from SAP scope — master_migration_summary_unified.md §2.
CreditController | credit/CreditoWeb_SaveFirstData | POST | WebApiMagento/Controllers/CreditController.cs:186 | WebApiMagento/Controllers/CreditController.cs:156 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/CreditoWeb_SaveData | POST | WebApiMagento/Controllers/CreditController.cs:404 | WebApiMagento/Controllers/CreditController.cs:417 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/CreditoWeb_SaveData_Articulos | POST | WebApiMagento/Controllers/CreditController.cs:208 | WebApiMagento/Controllers/CreditController.cs:170 | Unknown | Unknown | ANDROID | 0.00% | 0.00% | 0.00% | Planed Dev 1 | 8c5248a |  | Es android
CreditController | credit/CreditoWeb_Informacion | POST | WebApiMagento/Controllers/CreditController.cs:288 | WebApiMagento/Controllers/CreditController.cs:334 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/CreditoWeb_Solicitud | POST | WebApiMagento/Controllers/CreditController.cs:339 | WebApiMagento/Controllers/CreditController.cs:358 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/CreditoWeb_SolicitudPrimerGuardado | POST | WebApiMagento/Controllers/CreditController.cs:352 | WebApiMagento/Controllers/CreditController.cs:393 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/CreditoWeb_Seguro | POST | WebApiMagento/Controllers/CreditController.cs:386 | WebApiMagento/Controllers/CreditController.cs:405 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/GetCreditAmounts | POST | WebApiMagento/Controllers/CreditController.cs:314 | WebApiMagento/Controllers/CreditController.cs:346 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | CrediLana.
CreditController | credit/Validar_Lada | POST | WebApiMagento/Controllers/CreditController.cs:364 | WebApiMagento/Controllers/CreditController.cs:370 |  |  | ANDROID |  |  |  | Deprecated | 8c5248a |  | CrediLana.
CreditController | credit/codigoRecomendadoWithUen | POST | WebApiMagento/Controllers/CreditController.cs:256 | WebApiMagento/Controllers/CreditController.cs:199 |  |  | INTELISIS |  |  |  | Out of scope | 8c5248a |  | UEN variant; not in gap scope.
CreditController | credit/SaveImagesProductosMx | POST | WebApiMagento/Controllers/CreditController.cs:271 | WebApiMagento/Controllers/CreditController.cs:211 |  |  | EXT |  |  |  | Planed Dev 1 | 8c5248a |  | ProductosMX image upload.
CreditController | credit/GetPhoneValidatedClientSecretName | POST | WebApiMagento/Controllers/CreditController.cs:541 | WebApiMagento/Controllers/CreditController.cs:290 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | SMS/CrediLana family.
CreditController | credit/SendSmsNewNumber | POST | WebApiMagento/Controllers/CreditController.cs:548 | WebApiMagento/Controllers/CreditController.cs:302 |  |  | ANDROID |  |  |  | Planed Dev 1 | 8c5248a |  | SMS/CrediLana family.
CustomersController | customer/setCustomer | POST | WebApiMagento/Controllers/CustomersController.cs:14 | WebApiMagento/Controllers/CustomersController.cs:19 | partner/client | POST | SAP (BP01 ZAPI_BP01_PARTNER_SRV) | 100.00% | 100.00% | 100.00% | Migrated | c14b8c6 | 2026-07-15 | Bridge at DMZ CustomersController.cs:30. Route fully renamed. Returns BP number instead of Intelisis C-prefixed account.
CustomersController | customer/setCustomerList | POST | WebApiMagento/Controllers/CustomersController.cs:24 | WebApiMagento/Controllers/CustomersController.cs:41 | partner/client (batch) | POST | SIGMAVI + SAP | 0.00% | 0.00% | 0.00% | Not Migrated | b416730 |  | SpVTASListaNBMagento , SpVTASListaNBMagento, No se ha definido si la tabla se migrara a SAP o SigMavi para implementar logica
CustomersController | customer/getCustomerList | GET | WebApiMagento/Controllers/CustomersController.cs:54 | WebApiMagento/Controllers/CustomersController.cs:78 | partner/client/{clientId} | GET | SIGMAVI + SAP | 0.00% | 100.00% | 100.00% | Not Migrated | b416730 |  | Verb mismatch: DMZ declares [HttpGet], LAN declares [HttpPost], DMZ calls curl.Post. Pre-existing defect, not introduced by the migration.
CustomersController | customer/deleteCustomerList | POST | WebApiMagento/Controllers/CustomersController.cs:80 | WebApiMagento/Controllers/CustomersController.cs:96 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | b416730 |  | SpVTASListaNBMagento , SpVTASListaNBMagento
CustomersController | customer/cashCustomerReport | POST | WebApiMagento/Controllers/CustomersController.cs:108 | WebApiMagento/Controllers/CustomersController.cs:114 | Unknown | Unknown | OTRO | 0.00% | 0.00% | 0.00% | Planed Dev 1 | b416730 |  | @"\\172.16.200.2\mavica\ecom\BaseWhatsapp\STAGE\" + customerReportRequest.fileName, true);
CustomerServiceController | customerService/GetAccountDebts | POST | WebApiMagento/Controllers/CustomerServiceController.cs:99 | WebApiMagento/Controllers/CustomerServiceController.cs:129 | credit/GetAccountDebts | POST | SAP (EX01 ZAPI_EX01_NOCOMP_SRV) | 100.00% | 100.00% | 100.00% | Migrated | 9ec6be1 | 2026-07-24 | Bridge at DMZ CustomerServiceController.cs:137. Controller prefix changed customerService ? credit. See G-05.
CustomerServiceController | customerService/ApplyPaymentNeko | POST | WebApiMagento/Controllers/CustomerServiceController.cs:106 | WebApiMagento/Controllers/CustomerServiceController.cs:149 | credit/ApplyPaymentNeko | POST | SAP (ZFICRUD_COBREF_SRV) | 0.00% | 0.00% | 0.00% | In Progress | 9ec6be1 |  | es el api de ponce /sap/opu/odata/SAP/ZFICRUD_COBREF_SRV/WACOBREFSet, se comparte el wrapper
CustomerServiceController | customerService/UpdateStatusPaymentNeko | POST | WebApiMagento/Controllers/CustomerServiceController.cs:128 | WebApiMagento/Controllers/CustomerServiceController.cs:183 | credit/UpdateStatusPaymentNeko | POST | SAP (ZFICRUD_COBREF_SRV) | 0.00% | 0.00% | 0.00% | In Progress | 9ec6be1
CustomerServiceController | customerService/ApplyPaymentAdvanced | POST | WebApiMagento/Controllers/CustomerServiceController.cs:117 | WebApiMagento/Controllers/CustomerServiceController.cs:166 | Unknown | Unknown | SAP (ZFICRUD_COBREF_SRV — new) | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1
CustomerServiceController | customerService/UpdateStatusPaymentAdvanced | POST | WebApiMagento/Controllers/CustomerServiceController.cs:135 | WebApiMagento/Controllers/CustomerServiceController.cs:193 | Unknown | Unknown | SAP (ZFICRUD_COBREF_SRV) | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1
CustomerServiceController | customerService/obtenerTipoGarantia | POST | WebApiMagento/Controllers/CustomerServiceController.cs:15 | WebApiMagento/Controllers/CustomerServiceController.cs:21 | Unknown | Unknown | SIGMAVI | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | Preguntar quien llena la tabla VTASCProveedorActivoGarantia, para migrarla a sigmavi
CustomerServiceController | customerService/unirCuenta | POST | WebApiMagento/Controllers/CustomerServiceController.cs:37 | WebApiMagento/Controllers/CustomerServiceController.cs:50 | Unknown | Unknown | SAP (BP05 ? ZID_MAGENTO) | 0.00% | 100.00% | 100.00% | In Progress | 9ec6be1 |  | Unir, investigar api para update del cliente
CustomerServiceController | customerService/validarCliente | POST | WebApiMagento/Controllers/CustomerServiceController.cs:46 | WebApiMagento/Controllers/CustomerServiceController.cs:62 | partner/client/{clientId} | GET | SAP (BP05) | 0.00% | 100.00% | 100.00% | In Progress | 9ec6be1 |  | Strategy in dmz_orders_sap_mapping.md (Customer Service §1): replace the Cte table join with a BP05 lookup.
CustomerServiceController | customerService/nombreCliente | POST | WebApiMagento/Controllers/CustomerServiceController.cs:55 | WebApiMagento/Controllers/CustomerServiceController.cs:74 | partner/client/{clientId} | GET | SAP (BP05) | 0.00% | 100.00% | 100.00% | In Progress | 9ec6be1 |  | Same BP05 lookup.
CustomerServiceController | customerService/bitacoraAtencionClientes | POST | WebApiMagento/Controllers/CustomerServiceController.cs:68 | WebApiMagento/Controllers/CustomerServiceController.cs:90 | Unknown | Unknown | ANDROID (Sigmavi) |  |  |  | Planed Dev 1 | 9ec6be1 |  | Estimated 1/2/3 days, Dev 1.
CustomerServiceController | customerService/validarCoberturaPorCP | POST | WebApiMagento/Controllers/CustomerServiceController.cs:213 | WebApiMagento/Controllers/CustomerServiceController.cs:295 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | TABLE CodigoPostal , NO ESTA DEFINIDO LOS CP por proveedor de paqueteria, definir si se usa tabla z o tk11 transaccion de transportes, relacion con dtran08
CustomerServiceController | customerService/obtenerVentanaConfirmacion | POST | WebApiMagento/Controllers/CustomerServiceController.cs:24 | WebApiMagento/Controllers/CustomerServiceController.cs:33 | Unknown | Unknown | INTELISIS + (BP05) + (SD36) | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | FALTA LA api para obtener venta-entrega
CustomerServiceController | customerService/obtenerCreditos | POST | WebApiMagento/Controllers/CustomerServiceController.cs:77 | WebApiMagento/Controllers/CustomerServiceController.cs:103 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | TarjetaSerieMovMAVI , venta (sd36), articulos ya se tiene
CustomerServiceController | customerService/obtenerQuejas | POST | WebApiMagento/Controllers/CustomerServiceController.cs:86 | WebApiMagento/Controllers/CustomerServiceController.cs:115 | Unknown | Unknown | ANDROID | 0.00% | 0.00% | 0.00% | Planed Dev 1 | 9ec6be1
CustomerServiceController | customerService/ObtenerEstatusEmbarque | POST | WebApiMagento/Controllers/CustomerServiceController.cs:226 | WebApiMagento/Controllers/CustomerServiceController.cs:311 | Unknown | Unknown | INTELISIS | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | Consulta de SD08
CustomerServiceController | customerService/LoginClienteCredito | POST | WebApiMagento/Controllers/CustomerServiceController.cs:174 | WebApiMagento/Controllers/CustomerServiceController.cs:204 | Unknown | Unknown | INTELISIS |  |  |  | Out of scope | 9ec6be1 |  | CrediLana portal auth.
CustomerServiceController | customerService/LoginClienteCreditoFechaN | POST | WebApiMagento/Controllers/CustomerServiceController.cs:181 | WebApiMagento/Controllers/CustomerServiceController.cs:215 | Unknown | Unknown | INTELISIS |  |  |  | Out of scope | 9ec6be1 |  | CrediLana portal auth.
CustomerServiceController | customerService/GetSTPAccount | POST | WebApiMagento/Controllers/CustomerServiceController.cs:188 | WebApiMagento/Controllers/CustomerServiceController.cs:226 | Unknown | Unknown | EXT (STP) | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | Se nos proporcionara una api SAP para realizar la implementación (STP_API)
CustomerServiceController | customerService/GetSalesChannelsSTP | POST | WebApiMagento/Controllers/CustomerServiceController.cs:195 | WebApiMagento/Controllers/CustomerServiceController.cs:237 | Unknown | Unknown | EXT (STP) | 0.00% | 0.00% | 0.00% | Not Migrated | 9ec6be1 |  | CteEnviarA (STP_API)
CustomerServiceController | customerService/ValidateSTPAccount | GET | WebApiMagento/Controllers/CustomerServiceController.cs:202 | WebApiMagento/Controllers/CustomerServiceController.cs:248 | Unknown | Unknown | EXT (STP) | 0.00% | 0.00% | 0.00% | To Plan | 9ec6be1 |  | Se debe crear una tabla Z en SAP, consumir su API con el BP, clabe, y campo
CustomerServiceController | customerService/bbvaKeyNeko | POST | WebApiMagento/Controllers/CustomerServiceController.cs:142 | WebApiMagento/Controllers/CustomerServiceController.cs:258 | Unknown | Unknown | EXT (BBVA) | 0.00% | 0.00% | 0.00% | Deprecated | 9ec6be1 |  | API ALAN ISAI desarrollador punto de venta, ya no se consulta
CustomerServiceController | customerService/bbvaKeyAdvanced | POST | WebApiMagento/Controllers/CustomerServiceController.cs:158 | WebApiMagento/Controllers/CustomerServiceController.cs:275 | Unknown | Unknown | EXT (BBVA) | 0.00% | 0.00% | 0.00% | Planed Dev 1 | 9ec6be1 |  | API ALAN ISAI desarrollador punto de venta
CustomerServiceController | customerService/GetEmpleadoByNomina | POST | WebApiMagento/Controllers/CustomerServiceController.cs:236 | WebApiMagento/Controllers/CustomerServiceController.cs:367 | Unknown | Unknown | INTELISIS (payroll) |  |  |  | Out of scope | 9ec6be1 |  | Employee lookup; outside e-commerce scope.
CustomerServiceController | customerService/ActualizarCamposConfigurables | POST | Not in LAN - proxy target missing on both refs (G-07) | WebApiMagento/Controllers/CustomerServiceController.cs:327 |  |  | Unknown |  |  |  | Planed Dev 1 | 9ec6be1 |  | Dangling proxy — target absent from both stage-delta and origin/Production. See G-07.
CustomerServiceController | customerService/InsertarDesdeTablerateNativo | POST | Not in LAN - proxy target missing on both refs (G-07) | WebApiMagento/Controllers/CustomerServiceController.cs:339 |  |  | Unknown |  |  |  | Planed Dev 1 | 9ec6be1 |  | Dangling proxy. See G-07.
CustomerServiceController | customerService/InsertarDesdeTablerateCustom | POST | Not in LAN - proxy target missing on both refs (G-07) | WebApiMagento/Controllers/CustomerServiceController.cs:351 |  |  | Unknown |  |  |  | Planed Dev 1 | 9ec6be1 |  | Dangling proxy. See G-07.
LoginController | login/authenticate | POST | WebApiMagento/Controllers/LoginController.cs:17 | WebApiMagento/Controllers/LoginController.cs:17 | login/auth | POST | (local JWT) |  |  |  | Planed Dev 1 | 7f1b3dc |  | ServicioSAP exposes login/auth; the DMZ Curl constructor already authenticates against it. DMZ's own inbound route unchanged (correct — Magento's contract).
MagentoController | magento/attributes | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:14 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/general/attributes | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:22 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/attributeSets | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:30 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/attributeSetChildren/{id} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:38 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/categories | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:46 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/children/{page}/{size}/{store} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:54 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/noImagenProduct/{store} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:62 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/productWithWebsites/{page}/{size} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:70 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/getOrderId/{incrementId} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:78 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/deletePromociones | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:90 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/deleteReservations | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:103 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/getCuenta | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:112 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
MagentoController | magento/setCuenta | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/MagentoController.cs:121 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 6683489 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
OrdersController | order/setOrder | POST | WebApiMagento/Controllers/OrdersController.cs:138 | WebApiMagento/Controllers/OrdersController.cs:108 | order/new | POST | SAP (ZAPI_SALESORDER_SRV, SD01) | 100.00% | 100.00% | 100.00% | Migrated | 787de93 | 2026-03-31 | Bridge at DMZ OrdersController.cs:196. Legacy curl.Post("order/setOrder") retained at line 138 but unreachable — dead code.
OrdersController | order/cancelOrder | POST | WebApiMagento/Controllers/OrdersController.cs:186 | WebApiMagento/Controllers/OrdersController.cs:272 | order/cancelOrder | POST | SAP (SD46 — goods-issue reversal) | 70.00% | 100.00% | 100.00% | Migrated | d1b3d6e | 2026-07-23 | Bridge at DMZ OrdersController.cs:282. Author: ANGEL JAVIER RAMOS ALVARADO. Returns sentinel strings noexiste / ok.
OrdersController | order/returnOrder | POST | WebApiMagento/Controllers/OrdersController.cs:253 | WebApiMagento/Controllers/OrdersController.cs:301 | order/setreturn | POST | SAP (SD09 — returns/RMA) | 100.00% | 100.00% | 100.00% | Migrated | c14b8c6 | 2026-07-15 | Bridge at DMZ OrdersController.cs:317. Route renamed returnOrder ? setreturn.
OrdersController | order/getIntelisisStatuses | POST | WebApiMagento/Controllers/OrdersController.cs:93 | WebApiMagento/Controllers/OrdersController.cs:70 | (planned) order/getIntelisisStatuses | POST | SAP (SD36 ZAPI_DOCVTAS_CHECK_CDS) |  |  |  | Not Migrated | 8c5248a |  | Strategy fully specified in dmz_orders_sap_mapping.md §1; building block SalesMethods.CheckDocumentExistsSD36Async exists but no endpoint.
OrdersController | order/getPosCancellations | POST | WebApiMagento/Controllers/OrdersController.cs:113 | WebApiMagento/Controllers/OrdersController.cs:89 | order/cancelInvoice | POST | SAP (SD48 — invoice cancellation) |  |  |  | In Progress | 8c5248a |  | SAP side complete (5ef8d25, 2026-07-16). Estimated 5h/8h/2d, Dev 3. LAN counterpart exists on stage-delta but not on origin/Production — see G-18.
OrdersController | order/creditStatus/{idSolicitud} | GET | WebApiMagento/Controllers/OrdersController.cs:485 | WebApiMagento/Controllers/OrdersController.cs:461 | (planned) — reuse SD36 | GET | SAP (SD36 ? to_zsdt_vbak.Zidstatus) |  |  |  | Not Migrated | 8c5248a |  | Mapping documented in dmz_orders_sap_mapping.md §2 including the 01?Pendiente / 02?Concluido / 03?Anulado translation.
OrdersController | order/updateCreditOrderId | POST | WebApiMagento/Controllers/OrdersController.cs:507 | WebApiMagento/Controllers/OrdersController.cs:405 | Unknown | Unknown | Unknown |  |  |  | Planed Dev 1 | 8c5248a |  | Open technical question: SAP has not confirmed whether a PATCH to ZAPI_SALESORDER_SRV can rewrite the reference field. dmz_orders_sap_mapping.md §3.
OrdersController | order/estimated-delivery/{ecommerceId} | GET | WebApiMagento/Controllers/OrdersController.cs:536 | WebApiMagento/Controllers/OrdersController.cs:486 | Unknown | Unknown | INTELISIS (INVDPaqueteriaGuia) |  |  |  | Not Migrated | 8c5248a |  | Blocked. No SAP service identified to replace INVDPaqueteriaGuia. Unestimated.
OrdersController | order/GetPickUpCode | POST | WebApiMagento/Controllers/OrdersController.cs:347 | WebApiMagento/Controllers/OrdersController.cs:253 | Unknown | Unknown | INTELISIS (TrWDM0285_CteRecoge) |  |  |  | Not Migrated | 8c5248a |  | Blocked, unassigned. Business has not defined the clave venta PIN process. informe_estimaciones_gap.md §4.
OrdersController | order/ManagePaynetOrders | POST | WebApiMagento/Controllers/OrdersController.cs:22 | WebApiMagento/Controllers/OrdersController.cs:21 | (planned) | POST | SQLITE / INTELISIS (spAfectar) |  |  |  | Planed Dev 1 | 8c5248a |  | Depends on spAfectar, declared dead. Documents conflict on readiness — see G-08.
OrdersController | order/InsertPaymentData | POST | WebApiMagento/Controllers/OrdersController.cs:55 | WebApiMagento/Controllers/OrdersController.cs:52 | (planned) | POST | SQLITE (CXCCMensajeWebHookOpenPay) |  |  |  | Planed Dev 1 | 8c5248a |  | Requires SQLite/EF configured in ServicioSAP. See G-08.
OrdersController | order/getGuide | POST | WebApiMagento/Controllers/OrdersController.cs:164 | WebApiMagento/Controllers/OrdersController.cs:231 | (internal) SaveGuide |  | SQLITE |  |  |  | Planed Dev 1 | 8c5248a |  | master_migration_summary_unified.md §2.1 reports SaveGuide migrated to SQLite; no DMZ-facing route exposed.
OrdersController | order/validateCredit | POST | WebApiMagento/Controllers/OrdersController.cs:457 | WebApiMagento/Controllers/OrdersController.cs:370 |  |  | SAP (credit release, async callback) |  |  |  | In Progress | 8c5248a |  | Callback flow implemented in OrderMethods via VETA_URL_LIBERADOR / URL_DMZ; DMZ route not repointed.
OrdersController | order/authorizationResult | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/OrdersController.cs:422 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | DMZ?Magento notification. Not an Intelisis dependency.
OrdersController | order/setOrderStatus | POST | WebApiMagento/Controllers/OrdersController.cs:311 | WebApiMagento/Controllers/OrdersController.cs:325 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | Handler uses new Magento() directly; never reaches LAN.
OrdersController | order/getOrderInfo/{incrementId} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/OrdersController.cs:336 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | Magento-direct.
OrdersController | order/jsonOrders/{incrementId} | GET | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/OrdersController.cs:344 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | Magento-direct.
OrdersController | order/setCAccount | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/OrdersController.cs:358 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | Magento-direct.
OrdersController | order/sendStorePickupEmail | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/OrdersController.cs:242 |  |  | MAGENTO |  |  |  | Planed Dev 1 | 8c5248a |  | Magento-direct.
OrdersController | order/getprueba | GET | Not in LAN - DMZ-local diagnostic | WebApiMagento/Controllers/OrdersController.cs:38 | [6 empty] | Planed Dev 1 | 8c5248a |  | Diagnostic stub. Should not be exposed in production — see G-12.
ProductsController | product/updateProduct/{store} | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:26 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/updateConfigurableProduct/{store} | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:35 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/updateConfigurableProductLink/{sku} | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:44 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/updateStock | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:53 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/getStockByStore | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:62 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/updatePrice | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:69 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/uploadImage | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:78 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProductsController | product/uploadImagesToMagento | POST | Not in LAN - DMZ calls Magento REST directly | WebApiMagento/Controllers/ProductsController.cs:101 |  |  | MAGENTO |  |  |  | Planed Dev 1 | f516663 |  | Handled by new Magento() in the DMZ; calls the Magento REST API directly. Never reaches Intelisis.
ProspectoController | prospecto/rfc | POST | WebApiMagento/Controllers/ProspectoController.cs:19 | WebApiMagento/Controllers/ProspectoController.cs:15 | (candidate) partner/client/filter/{sapFilter} | GET | SAP (BP05) |  |  |  | In Progress | 3f74d24 |  | RFC lookup satisfiable by the BP filter endpoint.
ProspectoController | prospecto/recuperarcuenta | POST | WebApiMagento/Controllers/ProspectoController.cs:78 | WebApiMagento/Controllers/ProspectoController.cs:27 | (candidate) partner/client/filter/{sapFilter} | GET | SAP (BP05) |  |  |  | In Progress | 3f74d24 |  | Account recovery via BP05.
RecommenderController | recommender/setRecommenderList | POST | WebApiMagento/Controllers/RecomenderController.cs:15 | WebApiMagento/Controllers/RecommenderController.cs:21 | Unknown | Unknown | INTELISIS |  |  |  | Not Migrated | fa9aff5 |  | Resolves against stage-delta, not against origin/Production — see G-18. LAN filename is RecomenderController.cs (one m) but the class and [RoutePrefix("recommender")] both use two, so routing matches the DMZ.
RecommenderController | recommender/getRecommender | POST | WebApiMagento/Controllers/RecomenderController.cs:31 | WebApiMagento/Controllers/RecommenderController.cs:51 | Unknown | Unknown | INTELISIS |  |  |  | Not Migrated | fa9aff5 |  | As above. No SAP counterpart; absent from all gap documents (G-17).
RecommenderController | recommender/setCodes | POST | WebApiMagento/Controllers/RecomenderController.cs:41 | WebApiMagento/Controllers/RecommenderController.cs:62 | Unknown | Unknown | INTELISIS |  |  |  | Not Migrated | fa9aff5 |  | As above. No SAP counterpart; absent from all gap documents (G-17).
StatusController | status/getStatus | POST | WebApiMagento/Controllers/StatusController.cs:11 | WebApiMagento/Controllers/StatusController.cs:11 | Unknown |  | INTELISIS |  |  |  | Planed Dev 1 | be1d011 |  | LAN health probe. Verb mismatch: declared [HttpPost], calls curl.Get.
WalletCustomerController | customer/wallet/details | POST | WebApiMagento/Controllers/WalletCustomerController.cs:16 | WebApiMagento/Controllers/WalletCustomerController.cs:15 | customer/wallet/details | POST | SAP (SD18 ZAPI_CONDITIONCONTRACT_SRV) | 100.00% | 100.00% | 100.00% | Migrated | c14b8c6 | 2026-07-15 | Bridge at DMZ WalletCustomerController.cs:39. Route preserved verbatim — the cleanest mapping in the set.
WalletCustomerController | customer/wallet/getCuentaC/{ordenCompra} | GET | WebApiMagento/Controllers/WalletCustomerController.cs:40 | WebApiMagento/Controllers/WalletCustomerController.cs:52 | Unknown | Unknown | INTELISIS |  |  |  | Not Migrated | b416730 |  | Two defects: DMZ calls customer/getCuentaC/... — missing the /wallet segment present in the LAN [RoutePrefix]; and DMZ uses curl.Get while LAN declares [HttpPost]. See G-06.
WalletCustomerController | customer/wallet/getMinimumCostToRedeem | POST | WebApiMagento/Controllers/WalletCustomerController.cs:49 | WebApiMagento/Controllers/WalletCustomerController.cs:75 | (covered by) customer/wallet/details | POST | SAP (SD18) |  |  |  | In Progress | b416730 |  | Wallet data available from SAP; threshold logic not yet exposed as its own route.
WholesaleCustomerController | company/wholesale-customer/{wholesaleAccount} | GET | WebApiMagento/Controllers/WholesaleCustomerController.cs:15 | WebApiMagento/Controllers/WholesaleCustomerController.cs:17 | (candidate) product/articulos/ie/mayorista | GET | SAP (ZAPI_ARTICULOS_SRV) |  |  |  | In Progress | 763f14c |  | Wholesale article endpoint exists on SAP; customer-side not repointed.
WholesaleCustomerController | company/negotiable-quote/create | POST | WebApiMagento/Controllers/WholesaleCustomerController.cs:26 | WebApiMagento/Controllers/WholesaleCustomerController.cs:44 | Unknown | Unknown | INTELISIS |  |  |  | Deprecate | 763f14c |  | B2B negotiable quotes; no SAP mapping documented.
CustomersController (LAN-only) | customer/getCuenta | POST | WebApiMagento/Controllers/CustomersController.cs:90 | No DMZ route - LAN-only endpoint |  |  | MAGENTO (rest/V1/mavi-cuenta/getCuenta) |  |  |  | Planed Dev 1 | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
CustomersController (LAN-only) | customer/setCuenta | POST | WebApiMagento/Controllers/CustomersController.cs:99 | No DMZ route - LAN-only endpoint |  |  | MAGENTO (rest/V1/mavi-cuenta/setCuenta) |  |  |  | Planed Dev 1 | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
CreditController (LAN-only) | credit/SaveCredilanaInfo | POST | WebApiMagento/Controllers/CreditController.cs:453 | No DMZ route - LAN-only endpoint |  |  | INTELISIS (CredyPrestamoMethods) |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
OrdersController (LAN-only) | order/createStorepickupCode/{idEcommerce}/{idOrder} | POST | WebApiMagento/Controllers/OrdersController.cs:372 | No DMZ route - LAN-only endpoint | Unknown | Unknown | INTELISIS (CodigoRecogerSucursal / TrWDM0285_CteRecoge) |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
OrdersController (LAN-only) | order/generateNewStorepickupCode/{idEcommerce} | GET | WebApiMagento/Controllers/OrdersController.cs:394 | No DMZ route - LAN-only endpoint | Unknown | Unknown | INTELISIS (CodigoRecogerSucursal) |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
OrdersController (LAN-only) | order/getOrderId/{idEcommerce} | POST | WebApiMagento/Controllers/OrdersController.cs:417 | No DMZ route - LAN-only endpoint | Unknown | Unknown | INTELISIS (OrderMethods) + outbound Curl |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
OrdersController (LAN-only) | order/getOrderInfoAndSet/{incrementId} | GET | WebApiMagento/Controllers/OrdersController.cs:437 | No DMZ route - LAN-only endpoint |  |  | MAGENTO |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
OrdersController (LAN-only) | order/checkOpenpay | POST | WebApiMagento/Controllers/OrdersController.cs:446 | "webhook inverso" (LAN ? DMZ ? Magento) | Unknown | GET | SQLITE / INTELISIS (OpenpayMethods) |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updateProduct | POST | WebApiMagento/Controllers/ProductsController.cs:18 | "webhook inverso" (LAN ? DMZ ? Magento) | product/products, product/exportaart/{store} | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updateProductJsonOnly | POST | WebApiMagento/Controllers/ProductsController.cs:119 | "webhook inverso" (LAN ? DMZ ? Magento) | product/products | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updatePrice | POST | WebApiMagento/Controllers/ProductsController.cs:131 | "webhook inverso" (LAN ? DMZ ? Magento) | product/products | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updateConfigurableProduct | POST | WebApiMagento/Controllers/ProductsController.cs:144 | "webhook inverso" (LAN ? DMZ ? Magento) | product/jerarquia/articulos | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updateStockMavi | POST | WebApiMagento/Controllers/ProductsController.cs:162 | "webhook inverso" (LAN ? DMZ ? Magento) | product/stock | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/updateStock | POST | WebApiMagento/Controllers/ProductsController.cs:178 | "webhook inverso" (LAN ? DMZ ? Magento) | product/stock | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/getStockByStore | POST | WebApiMagento/Controllers/ProductsController.cs:193 | No DMZ route - LAN-only endpoint | product/stock/filter/{filter} | GET | INTELISIS |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
ProductsController (LAN-only) | product/existenciasAlmacenArt | POST | WebApiMagento/Controllers/ProductsController.cs:203 | "webhook inverso" (LAN ? DMZ ? Magento) | product/stock/filter/{filter} | GET | INTELISIS |  |  |  | Planed Dev 2 | 7c46e13 |  | Job del servidor LAN, ImportApp - Microsoft Team Foundation Server
ProductsController (LAN-only) | product/obtenerImagen | POST | WebApiMagento/Controllers/ProductsController.cs:215 | No DMZ route - LAN-only endpoint | ma/imagenes/optimizadas | GET | INTELISIS |  |  |  | Out of scope | 7c46e13 |  | No tiene ruta en DMZ, no lo consulta magento pero lo puede consultar otra aplicación, se desconoce.
MercanciaController | mercancias/getAbonos | POST | WebApiMagento/Controllers/MercanciaController.cs:17 | WebApiMagento/Controllers/MercanciaController.cs:16 | (candidate) credit/GetAccountDebts | POST | SAP (EX01/TZ01) |  |  |  | Deprecated | 5f00c8f |  | RESTORED - absent from the hand-scored copy; percentages not yet set. LAN handler carries // TODO: Query pendiente de ERP (MercanciaMethods.cs:187) — incomplete even in LAN.
MercanciaController | mercancias/getProximosPagos | POST | WebApiMagento/Controllers/MercanciaController.cs:26 | WebApiMagento/Controllers/MercanciaController.cs:31 | (candidate) credit/GetAccountDebts | POST | SAP (EX01) |  |  |  | Deprecated | 5f00c8f |  | RESTORED - absent from the hand-scored copy; percentages not yet set. Open FI items available via EX01.
MercanciaController | mercancias/getSaldoVencido | POST | WebApiMagento/Controllers/MercanciaController.cs:35 | WebApiMagento/Controllers/MercanciaController.cs:51 | (candidate) credit/GetAccountDebts | POST | SAP (EX01) |  |  |  | Deprecated | 5f00c8f |  | RESTORED - absent from the hand-scored copy; percentages not yet set. Overdue balance derivable from EX01 open items.
MercanciaController | mercancias/getLimiteMercancia | POST | WebApiMagento/Controllers/MercanciaController.cs:44 | WebApiMagento/Controllers/MercanciaController.cs:74 | (candidate) partner/client/{clientId} | GET | SAP (BP05 ZlimCred) |  |  |  | Deprecated | 5f00c8f |  | RESTORED - absent from the hand-scored copy; percentages not yet set. Credit limit exposed on BP05.
MercanciaController | mercancias/ValidarTelefono | POST | WebApiMagento/Controllers/MercanciaController.cs:53 | WebApiMagento/Controllers/MercanciaController.cs:88 | (candidate) partneraddress/partner/phone | PATCH | SAP (BP address to_PhoneNumber) |  |  |  | Deprecated | 5f00c8f |  | RESTORED - absent from the hand-scored copy; percentages not yet set. Phone handling built in PartnerAddressController.